## Sheet1
Phase | Phase Name | Task | Task ID | Task Description | Estimated Hours | Actual Hours | Estimated Cost (CHF) | Actual Cost (CHF)
1 | Simulation | 1 | T_1_1 | Grasp and understand the kninematics | 10 | 12 | 0 | 0
|  | 2 | T_1_2 | Create a numerical twin in simscape | 12 | 18 | 0 | 0
|  | 3 | T_1_3 | optimise arm lengths and tune PID | 4 | 2 | 0 | 0
|  | 4 | T_1_4 | Take and read force valeus seen by the system | 6 | 2 | 0 | 0
|  | 5 | T_1_5 | do some rough FEMM simulations to test feasability | 10 | 4 | 0 | 0
T_1_6
|  | 6 | T_1_7
|  | 7 | T_1_TOT |  | 42 | 38 | 0 | 0
2 | Mechanical & Electronics Design | 1 | T_2_1 | Motor Selection and Purchases | 8 | 8 | 400
|  | 2 | T_2_2 | Frame | 4 | 12 | 400
|  | 3 | T_2_3 | Motor to Arm linkage | 2 |  | 50
|  | 4 | T_2_4 | Bicep | 4 |  | 50 |  | Task ID | Phase | Task Description | Estimated Hours | Actual Hours | Variance (Hours) | Estimated Cost (CHF) | Actual Cost (CHF)
|  | 5 | T_2_5 | Forearm (Ball joint incl.) | 6 |  | 100 |  | T1 | Simulation & Design | Kinematic & Dynamic Modeling in Simulink | 30 | 0 | 30 | #ERROR! | A2\ | Bill_of_Materials!F:F) | 0
|  | 6 | T_2_6 | Effector | 8 |  | 60 |  | T2 | Simulation & Design | Path Generation & Trajectory Smoothing (S-Curve/30G Optimization) | 20 | 0 | 20 | #ERROR! | A3\ | Bill_of_Materials!F:F) | 0
|  | 7 | T_2_7 | Saftey Critical Features | 8 |  | 100 |  | T3 | Mechanical | Procurement of 80x80 Profiles and Hardware | 10 | 0 | 10 | #ERROR! | A4\ | Bill_of_Materials!F:F) | 0
|  | 8 | T_2_8 | PLC | 16 |  | 400 |  | T4 | Mechanical | Machining & Mounting 10mm HPL Vulcano Base Plate | 15 | 0 | 15 | #ERROR! | A5\ | Bill_of_Materials!F:F) | 0
|  | 9 | T_2_9 | PLC I/O | 4 |  | 100 | 153 | T5 | Mechanical | Assembling Carbon Fiber Arms & Ball Joints (150mm/300mm) | 12 | 0 | 12 | #ERROR! | A6\ | Bill_of_Materials!F:F) | 0
|  | 10 | T_2_10 | [5 empty] | T6 | Electronics | Wiring StepperOnline T6 Servos & Power Supplies | 15 | 0 | 15 | #ERROR! | A7\ | Bill_of_Materials!F:F) | 0
|  | 11 | T_2_11 | [5 empty] | T7 | Electronics | Implementing DC E-Stop Safety & Mechanical Brakes | 8 | 0 | 8 | #ERROR! | A8\ | Bill_of_Materials!F:F) | 0
|  | 12 | T_2_12 | [5 empty] | T8 | Control & EtherCAT | Setting up TwinCAT 3 Real-Time Kernel on Legion Laptop | 25 | 0 | 25 | #ERROR! | A9\ | Bill_of_Materials!F:F) | 0
|  | 13 | T_2_13 | [5 empty] | T9 | Control & EtherCAT | Mapping Drive ESI Files & Tuning 17-bit CSP Loops | 20 | 0 | 20 | #ERROR! | A10\ | Bill_of_Materials!F:F) | 0
|  | 14 | T_2_14 | [5 empty] | T10 | Academic | Website Documentation & Final Project Report Writing | 40 | 0 | 40 | #ERROR! | A11\ | Bill_of_Materials!F:F) | 0
|  | 14 | T_2_TOT |  | 60 | 20 | 1660 | 153 | T10 | Academic | Website Documentation & Final Project Report Writing | 40 | 0 | 40 | #ERROR! | A11\ | Bill_of_Materials!F:F) | 0
[9 empty] | TOTAL |  | Total Project Summary | 195 | 0 | 195 | #ERROR! | 0
#ERROR!
[9 empty] | Part ID | Component Name | Supplier | Qty | Unit Cost (CHF) | Total Cost (CHF) | Link to Task ID | Status
[9 empty] | P1 | StepperOnline T6 EtherCAT Servo Motors + Drives (400W) | StepperOnline | 3 | 120 | 0 | T6 | Ordered
[9 empty] | P2 | 80x80 Aluminum Profiles & Fasteners | Local Supplier | 1 | 90 | 0 | T3 | Planned
[9 empty] | P3 | 10mm HPL Vulcano Base Plate | Local Supplier | 1 | 45 | 0 | T4 | Planned
[9 empty] | P4 | Carbon Fiber Tubes & High-Precision Ball Joints | Aliexpress/Hobby | 1 | 50 | 0 | T5 | Planned
[9 empty] | P5 | Heavy Duty DC Power Supply (Drive Power) | Distrelec | 1 | 65 | 0 | T6 | Planned
[9 empty] | P6 | Latching E-Stop Button + Safety Contactor | Distrelec | 1 | 25 | 0 | T7 | Planned
[9 empty] | P7 | Shielded Cat6 SFTP Cables (EtherCAT Network) | Local Shop | 4 | 5 | 0 | T8 | Planned
[9 empty] | P8 | Misc. Hardware (M8 Bolts\ | T-Nuts\ | Cable Ties) | Hardware Store | 1 | 20 | 0 | T3 | Planned